## PMO tracker_Jaipur
2022-05-18
| State | AO | District | Taluka | Activity theme | Activity | Person responsible | Start date | Target- End date | Actual- End date | Status
| RJ-1 (Jaipur) | Alwar | Alwar | ALWAR | Cement Xpress
| RJ-1 (Jaipur) | Alwar | Alwar | ALWAR | Mini-depot to prospective dealer | [6 empty] | Cement Xpress | On-going
| RJ-1 (Jaipur) | Alwar | Alwar | ALWAR | Tranformative branding | [6 empty] | Contractor scheme | Delayed
| RJ-1 (Jaipur) | Alwar | Alwar | ALWAR | [7 empty] | Mini-depot to prospective dealer | Completed
| RJ-1 (Jaipur) | Alwar | Alwar | ALWAR | [7 empty] | CS/SS for taluka
| RJ-1 (Jaipur) | Alwar | Alwar | ALWAR | [7 empty] | City express
| RJ-1 (Jaipur) | Alwar | Alwar | ALWAR | [7 empty] | New warehouse
| RJ-1 (Jaipur) | Alwar | Alwar | ALWAR | [7 empty] | Tranformative branding
| RJ-1 (Jaipur) | Alwar | Alwar | ALWAR | [7 empty] | IBH Buniyaad
| RJ-1 (Jaipur) | Alwar | Alwar | ALWAR | [7 empty] | Dealer onboarding scheme
| RJ-1 (Jaipur) | Alwar | Alwar | ALWAR | [7 empty] | Family engagement event
| RJ-1 (Jaipur) | Alwar | Alwar | ALWAR | [7 empty] | Dedicated BTL van activity
| RJ-1 (Jaipur) | Alwar | Alwar | ALWAR | [7 empty] | Contractor name branding
| RJ-1 (Jaipur) | Alwar | Alwar | ALWAR | [7 empty] | ARS interest generation meet
| RJ-1 (Jaipur) | Alwar | Alwar | BEHROR | [7 empty] | Satellite counter
| RJ-1 (Jaipur) | Alwar | Alwar | TIJARA | [7 empty] | Shoorveer redemption drive
| RJ-1 (Jaipur) | Alwar | BHARATPUR | NAGAR | [7 empty] | Vehicle finance
| RJ-1 (Jaipur) | Alwar | DHOLPUR | DHOLPUR | IBH Buniyaad | 2 leads are there for dealer onboarding scheme | Krishna Gavhane |  |  |  |  | Market combing
| RJ-1 (Jaipur) | Alwar | DHOLPUR | DHOLPUR | Contractor scheme | Silver scheme will be distributed among contractors through BO Budget | Krishna Gavhane | 22/5/2022 | 2022-08-01 |  |  | Market combing
| RJ-1 (Jaipur) | Alwar | DHOLPUR | DHOLPUR | Family engagement event | A get to gather function will be done for developing relation between contractors | Krishna Gavhane | 22/5/2022 | 2022-06-15 |  |  | Market combing
| RJ-1 (Jaipur) | Alwar | DHOLPUR | DHOLPUR | Dedicated BTL van activity | BTL activity in Dholpur rural areas and city . | Krishna Gavhane | 22/6/2022 | 2022-07-03 |  |  | Market combing
| RJ-1 (Jaipur) | Alwar | DHOLPUR | DHOLPUR | Market combing | BTL activity in Dholpur rural areas and city . | Krishna Gavhane | 22/6/2022 | 2022-06-01 |  |  | Market combing
| RJ-1 (Jaipur) | Alwar | DHOLPUR | DHOLPUR | Contractor name branding | Will provide boards to contractors | Krishna Gavhane | 22/5/2022 | 2022-06-18 |  |  | Market combing
| RJ-1 (Jaipur) | Alwar | DHOLPUR | DHOLPUR | ARS interest generation meet | A function to create new leads | Krishna Gavhane | 19/5/2022 | 2022-06-05 |  |  | Market combing
| RJ-1 (Jaipur) | Alwar | DHOLPUR | RAJAKHERA | Dealer onboarding scheme | 2 leads are there for dealer onboarding scheme | Krishna Gavhane | 22/5/2022 | 2022-08-06 |  |  | BO Revamp
| RJ-1 (Jaipur) | Alwar | DHOLPUR | RAJAKHERA | Family engagement event | A get to gather function will be done for developing relation between contractors | Krishna Gavhane | 22/5/2022 | 2022-06-17 |  |  | BO Revamp
| RJ-1 (Jaipur) | Alwar | DHOLPUR | RAJAKHERA | Contractor scheme | Silver scheme will be distributed among contractors through BO Budget | Krishna Gavhane | 22/5/2022 | 2022-07-01 |  |  | BO Revamp
| RJ-1 (Jaipur) | Alwar | DHOLPUR | RAJAKHERA | Dedicated BTL van activity | BTL activity is required in nearby rural areas of Rajakheda , Machariya ,Marena , Jatoli , Mangrol . | Krishna Gavhane | 22/5/2022 | 2022-06-03 |  |  | BO Revamp
| RJ-1 (Jaipur) | Alwar | DHOLPUR | RAJAKHERA | Contractor name branding | - | Krishna Gavhane | 22/5/2022 | 2022-06-15 |  |  | BO Revamp
| RJ-1 (Jaipur) | Alwar | DHOLPUR | RAJAKHERA | ARS interest generation meet | To create new leads a function for other brand retailers will be done | Krishna Gavhane | 19/5/2022 | 2022-06-04 |  |  | BO Revamp
| RJ-1 (Jaipur) | Alwar | DHOLPUR | RAJAKHERA | Market combing | In combing visits will be done on counters and sites of whitespace areas | Krishna Gavhane | 20/5/2022 | 28/5/2022 |  |  | BO Revamp
| RJ-1 (Jaipur) | Jaipur | Jaipur | Chomu
| RJ-1 (Jaipur) | Jaipur | Jaipur | Jaipur
| RJ-1 (Jaipur) | Jaipur | Jaipur | Kotputli
| RJ-1 (Jaipur) | Jaipur | Jaipur | Phagi
| RJ-1 (Jaipur) | Jaipur | Jaipur | Phulera
| RJ-1 (Jaipur) | Jaipur | Jaipur | Sanganer
| RJ-1 (Jaipur) | Jaipur | Jaipur | SHAHPURA
| RJ-1 (Jaipur) | Jaipur Rural | Dausa | Baswa | Contractor scheme | Bandikui- silver & white goods (kind) for 1 quarter funded by BO | Bharat Bhushan | 2022-05-23 | 2022-06-01
| RJ-1 (Jaipur) | Jaipur Rural | Dausa | Baswa | New warehouse | Manpura- 800 MT nearby Sikrai | Bharat Bhushan | 2022-05-25 | 2022-07-05
| RJ-1 (Jaipur) | Jaipur Rural | Dausa | Baswa | IBH Buniyaad | Bandikui- 30 IHB | Bharat Bhushan | 2022-06-15 | 2022-07-05
| RJ-1 (Jaipur) | Jaipur Rural | Dausa | Baswa | Family engagement event | Bandikui- 30 families of contractors; Shoorveer attachment | Bharat Bhushan | 2022-06-12 | 2022-06-12
| RJ-1 (Jaipur) | Jaipur Rural | Dausa | Baswa | Contractor name branding | Bandikui- Top 10 contractors name branding (Board) | Bharat Bhushan | 2022-06-15 | 2022-07-14
| RJ-1 (Jaipur) | Jaipur Rural | Dausa | Baswa | ARS interest generation meet | Godakatla, Golada, Bandikui- Identification + Lunch | Bharat Bhushan | 2022-07-05 | 2022-07-20
| RJ-1 (Jaipur) | Jaipur Rural | Dausa | Baswa | Shoorveer redemption drive | Top 30 contractors > 5000 points | Bharat Bhushan | 2022-05-23 | 2022-06-10
| RJ-1 (Jaipur) | Jaipur Rural | Dausa | Baswa | Market combing | Bandikui- local; Contractor (80); ARS (5) | Bharat Bhushan | 2022-06-15
| RJ-1 (Jaipur) | Jaipur Rural | Dausa | Dausa
| RJ-1 (Jaipur) | Jaipur Rural | Dausa | Lalsot
| RJ-1 (Jaipur) | Jaipur Rural | Dausa | Sikrai