## Dashboard
Count of District | Column Labels |  | Count of District | Column Labels
Districts | Ongoing | Grand Total | Districts | Ongoing | Grand Total
NAGAR | 9 | 9 | Alwar | 44 | 44
SHAHPURA | 8 | 8 | Jaipur | 52 | 52
Phagi | 8 | 8 | Jaipur Rural | 27 | 27
Baswa | 8 | 8 | Grand Total | 123 | 123
Kotputli | 8 | 8
Chomu | 8 | 8
Dausa | 8 | 8
Sanganer | 8 | 8
ALWAR | 7 | 7
RAJAKHERA | 7 | 7
BEHROR | 7 | 7
DHOLPUR | 7 | 7
TIJARA | 7 | 7
Jaipur | 7 | 7
Lalsot | 6 | 6
Phulera | 5 | 5
Sikrai | 5 | 5
Grand Total | 123 | 123

## PMO tracker_Jaipur
2022-11-05
| State | AO | District | Taluka | Activity theme | Activity | Person responsible | Start date | Target- End date | Actual- End date | Status
| RJ-1 (Jaipur) | Jaipur | Jaipur | Jaipur | Contractor scheme | Short Term Scheme in silver or Kind | Nikhlesh Sharma, Anish Chajed | 2022-06-01 | 2022-07-30 |  | Delayed | Ongoing
| RJ-1 (Jaipur) | Jaipur | Jaipur | Jaipur | Dealer onboarding scheme | May- Dealer (1), ARS (1); June- Dealer (3), ARS (5) | Nikhlesh Sharma | 2022-06-01 | 2022-06-30 |  | Ongoing | Completed
| RJ-1 (Jaipur) | Jaipur | Jaipur | Jaipur | Market combing | Benad road, Kalwa road, Sirsi road; Dealer (50); ARS (150); Contractor (250+) | Nikhlesh Sharma, Anish Chajed | 2022-06-05 | 2022-06-10 |  | Ongoing | Delayed
| RJ-1 (Jaipur) | Jaipur | Jaipur | Jaipur | IBH Buniyaad | IHB Meet; 20-25 IHBs -> Slab observance etc. basis their upcoming construction | Anish Chajed | 2022-06-10 | 2022-06-15 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur | Jaipur | Jaipur | ARS interest generation meet | 20-25 ARS - 2 parts | Nikhlesh Sharma | 2022-06-20 | 2022-06-30 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur | Jaipur | Jaipur | Family engagement event | 15+ contractors; 30 people | Anish Chajed | 2022-07-05 | 2022-07-10 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur | Jaipur | Jaipur | BO Revamp | Market visit along with BO for new dealers , Contractor schemes and increse sale in white space places | Nikhlesh Sharma | 2022-06-01 | 2022-06-30 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur | Jaipur | Sanganer | Contractor scheme | Short Term Scheme in silver or Kind | Yashkant Tripathi, Anish Chajed | 2022-06-01 | 2022-07-30 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur | Jaipur | Sanganer | Dealer onboarding scheme | May- Dealer (1), ARS (2); June- Dealer (3), ARS (5) | Yashkant Tripathi | 2022-06-01 | 2022-06-30 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur | Jaipur | Sanganer | Market combing | Vatika, Pratapgarh, Sitapura; Dealer (40), ARS (100), Contractor (200) | Yashkant Tripathi, Anish Chajed | 2022-06-10 | 2022-06-15 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur | Jaipur | Sanganer | IBH Buniyaad | IHB Meet for pre and post slab supervision by CTS | Anish Chajed | 2022-06-15 | 2022-06-20 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur | Jaipur | Sanganer | ARS interest generation meet | To adding for some new ars from other brands | Yashkant Tripathi | 2022-06-15 | 2022-06-20 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur | Jaipur | Sanganer | Family engagement event | To create brand pull threw relationshiop with contractors | Anish Chajed | 2022-07-05 | 2022-07-10 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur | Jaipur | Sanganer | New warehouse | To open New warehouse at vatika | Yashkant Tripathi | 2022-05-18 | 2022-06-10 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur | Jaipur | Sanganer | BO Revamp | Market visit along with BO for new dealers , Contractor schemes and increse sale in white space places | Yashkant Tripathi | 2022-06-01 | 2022-06-30 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | Alwar | ALWAR | Dealer onboarding scheme | local alwar; Dealers (2), ARS (7), and rural; Dealer (1), ARS (3) | Sumit Verma | 2022-05-25 | 2022-06-30 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | Alwar | ALWAR | Shoorveer redemption drive | Top 50 contractors > 5000 points | Saurav Goyal, Sumit Verma | 2022-05-25 | 2022-06-16 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | Alwar | ALWAR | Family engagement event | 30 families of contractors; Shoorveer attachment | Sumit Verma | 2022-05-26 | 2022-06-18 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | Alwar | ALWAR | IBH Buniyaad | Alwar Local 35 Couple IHB | Saurav Goyal, Sumit Verma | 2022-06-01 | 2022-07-20 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | Alwar | ALWAR | Contractor scheme | Silver (kind) for 1 quarter; 200 bags, 5 gm | Saurav Goyal, Sumit Verma | 2022-05-24 | 2022-10-10 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | Alwar | ALWAR | ARS interest generation meet | Rural area of alwar taluka new prospect ars meeting 20 pax | Harish Yadav, Sumit Verma | 2022-06-02 | 2022-06-18 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | Alwar | ALWAR | Market combing | 3 batches; Dealer (75), ARS (100), Contractor (200+) | Sumit Verma | 2022-05-22 | 2022-06-30 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | Alwar | BEHROR | Contractor scheme | SILVER SCHEME- BO budget | Vipul Garg/Saurav Goyal | 2022-06-05 | 2022-10-10 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | Alwar | BEHROR | IBH Buniyaad | 30 TO 40 IHB FROM BEHROR AND NEAREST AREA | Vipul Garg/Saurav Goyal | 2022-05-30 | 2022-07-22 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | Alwar | BEHROR | Dealer onboarding scheme | SCHEME TO APPOINT NETWORK IN VACANT MARKET; Dealer (5), ARS (10) | Vipul Garg/Saurav Goyal | 2022-05-18 | 2022-06-30 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | Alwar | BEHROR | Family engagement event | ENGAGEMENT EVENT OF CONTRACTORS (25-30) | Vipul Garg/Saurav Goyal | 2022-05-24 | 2022-06-19 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | Alwar | BEHROR | ARS interest generation meet | PLAN TO CONDUCT A.R.S MEET (30-35); Self + competitor ARS | Vipul Garg/Saurav Goyal | 2022-06-10 | 2022-06-16 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | Alwar | BEHROR | Shoorveer redemption drive | Top 50 contractors > 5000 points | Vipul Garg/Saurav Goyal | 2022-05-26 | 2022-06-16 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | Alwar | BEHROR | Market combing | VACANT MARKET IN TALUKA; Dealer (75), ARS (125), Contractor (120 sites) | Vipul Garg/Saurav Goyal | 2022-05-28 | 2022-06-06 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | Alwar | TIJARA | Dealer onboarding scheme | SCHEME TO APPOINT NETWORK IN VACANT MARKET; Dealer (2), ARS (6) | Vipul Garg/Saurav Goyal | 2022-05-20 | 2022-06-30 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | Alwar | TIJARA | Shoorveer redemption drive | Top 30 contractors > 5000 points | Vipul Garg/Saurav Goyal | 2022-05-24 | 2022-06-14 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | Alwar | TIJARA | IBH Buniyaad | 30 TO 40 IHB FROM BHIWADI AND NEAREST AREA | Vipul Garg/Saurav Goyal | 2022-05-20 | 2022-06-15 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | Alwar | TIJARA | Contractor scheme | SILVER SCHEME- BO funded | Vipul Garg/Saurav Goyal | 2022-06-01 | 2022-07-30 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | Alwar | TIJARA | ARS interest generation meet | A.R.S MEET FROM BHIWADI,TIJARA; 25-30 ARS | Vipul Garg/Saurav Goyal | 2022-06-02 | 2022-06-18 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | Alwar | TIJARA | New warehouse | TIJARA | Vipul Garg/Saurav Goyal | 2022-06-15 | 2022-08-01 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | Alwar | TIJARA | Market combing | VACANT MARKET IN TIJARA TALLUKA; Dealer (35), ARS (70), Contractor (100) | Vipul Garg/Saurav Goyal | 2022-05-22 | 2022-06-05 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | BHARATPUR | NAGAR | Dealer onboarding scheme | FEW PARTIES ARE IN PROSPECT,THIS WILL HELP TO CONVERT THEM; Dealer (), ARS (), Contractor () | Manish Agarwal/Rohit Sharma | 2022-05-30 | 2022-06-15 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | BHARATPUR | NAGAR | Contractor scheme | SILVER SCHEME | Manish Agarwal/Rohit Sharma | 2022-06-15 | 2022-09-01 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | BHARATPUR | NAGAR | Dedicated BTL van activity | WILL PLAN OF BTL IN NAGAR TALUKA FOR HYPE MARKETING, WILL GET HELP TO APPOINT NEW DEALER. | Manish Agarwal/Rohit Sharma | 2022-05-22 | 2022-06-02 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | BHARATPUR | NAGAR | Satellite counter | WILL DISCUSS WITH BO & START A SATELITE COUNTER TILL DEALER WILL NOT APPOINT | Manish Agarwal/Rohit Sharma | 2022-05-30 | 2022-06-22 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | BHARATPUR | NAGAR | Contractor name branding | WILL TAKE HELP OF THIS TOOL FOR ONBOARD HIGH POTENTIAL CONTRACTORS | Manish Agarwal/Rohit Sharma | 2022-05-25 | 2022-06-20 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | BHARATPUR | NAGAR | ARS interest generation meet | WILL VISIT & RETAIL OUTLETS OF THE TALUKA & GATHER THEM FOR A PROMOTIONAL MEETING TO ASSOCIATE THEM WITH US. | Manish Agarwal/Rohit Sharma | 2022-06-10 | 2022-06-26 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | BHARATPUR | NAGAR | New warehouse | FOR THE SAME TALUKA & NEARBY DESTINATIONS. | Manish Agarwal/Rohit Sharma | 2022-05-25 | 2022-06-30 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | BHARATPUR | NAGAR | Market combing | WILL PLAN 2 COMBING,ONE FOR NETWORK MAPPING THEN SITE MAPPING COMBING. | Manish Agarwal/Rohit Sharma | 2022-05-25 | 2022-06-04 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | BHARATPUR | NAGAR | BO Revamp | PLAN TO IDENTIFY PARTIES FOR BO & WANT TO START WORK WITH NEW BO | Manish Agarwal/Rohit Sharma | 2022-05-30 | 2022-06-10 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | DHOLPUR | DHOLPUR | IBH Buniyaad | Existing (30+) + New onboards (40+) | Krishna Gavhane | 2022-05-30 | 2022-06-30 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | DHOLPUR | DHOLPUR | Contractor scheme | Silver scheme will be distributed among contractors through BO Budget | Krishna Gavhane | 2022-06-01 | 2022-07-30 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | DHOLPUR | DHOLPUR | Family engagement event | 50+ contractors activity for 100 people | Krishna Gavhane | 2022-06-01 | 2022-06-15 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | DHOLPUR | DHOLPUR | Dedicated BTL van activity | BTL activity in Dholpur rural areas and city . | Krishna Gavhane | 2022-06-22 | 2022-07-03 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | DHOLPUR | DHOLPUR | Market combing | Dholpur + Rajakhera; Dealer (80), ARS (160), Contractor (100+) | Krishna Gavhane | 2022-06-22 | 2022-06-01 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | DHOLPUR | DHOLPUR | Contractor name branding | Will provide boards to contractors | Krishna Gavhane | 2022-05-22 | 2022-06-18 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | DHOLPUR | DHOLPUR | ARS interest generation meet | ARS meet: 25-30 leads -> Onboarding target (4) | Krishna Gavhane | 2022-05-19 | 2022-06-15 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | DHOLPUR | RAJAKHERA | Dealer onboarding scheme | Dealer (1), ARS (2) target by end Jun '22 | Krishna Gavhane | 2022-05-22 | 2022-06-30 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | DHOLPUR | RAJAKHERA | Family engagement event | 50+ contractors activity not family, logistics issue | Krishna Gavhane | 2022-05-22 | 2022-06-17 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | DHOLPUR | RAJAKHERA | Contractor scheme | Silver scheme will be distributed among contractors through BO Budget | Krishna Gavhane | 2022-05-22 | 2022-07-01 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | DHOLPUR | RAJAKHERA | Dedicated BTL van activity | BTL activity is required in nearby rural areas of Rajakheda , Machariya ,Marena , Jatoli , Mangrol . | Krishna Gavhane | 2022-06-15 | 2022-06-30 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | DHOLPUR | RAJAKHERA | Contractor name branding | Information sent to marketing | Krishna Gavhane | 2022-05-22 | 2022-06-15 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | DHOLPUR | RAJAKHERA | ARS interest generation meet | ARS meet: 25-30 leads -> Onboarding target (4) | Krishna Gavhane | 2022-05-19 | 2022-06-04 |  | Ongoing
| RJ-1 (Jaipur) | Alwar | DHOLPUR | RAJAKHERA | Market combing | Dholpur + Rajakhera; Dealer (80), ARS (160), Contractor (100+) | Krishna Gavhane | 2022-05-20 | 2022-05-28 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Jaipur | Chomu | Dealer onboarding scheme | Dealer Appointment target approx - 2 | Varun Jha | 2022-05-20 | 2022-05-31 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Jaipur | Chomu | Shoorveer redemption drive | Top 30 contractors > 5000 points | Varun Jha, Sunil Chaudhary | 2022-06-02 | 2022-06-05 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Jaipur | Chomu | IBH Buniyaad | CHOMU- 30 IHB | Varun Jha, Sunil Chaudhary | 2022-05-27 | 2022-05-27 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Jaipur | Chomu | Family engagement event | CHOMU - 30 families of contractors; Shoorveer attachment | Varun Jha, Sunil Chaudhary | 2022-07-25 | 2022-07-25 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Jaipur | Chomu | Contractor scheme | CHOMU`- silver & white goods (kind) for 1 quarter funded by BO | Varun Jha, Sunil Chaudhary | 2022-06-15 | 2022-10-15 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Jaipur | Chomu | Dedicated BTL van activity | BTL Van for CHOMU tehsil | Varun Jha | 2022-07-01 | 2022-07-08 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Jaipur | Chomu | ARS interest generation meet | CHOMU, DODOSAR, KHEEJROLI- Identification + Lunch | Varun Jha, Sunil Chaudhary | 2022-06-20 | 2022-07-10 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Jaipur | Chomu | Contractor name branding | CHOMU- Top 10 contractors name branding (Board) | Varun Jha | 2022-05-20 | 2022-06-10 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Jaipur | Kotputli | Dealer onboarding scheme | Dealer Appointment target approx - 1 | Avinash Gautam | 2022-05-20 | 2022-05-31 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Jaipur | Kotputli | IBH Buniyaad | KOTPUTLI- 30 IHB | Avinash Gautam, Akash Rathore | 2022-07-10 | 2022-07-28 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Jaipur | Kotputli | Shoorveer redemption drive | Top 30 contractors > 5000 points | Avinash Gautam, Akash Rathore | 2022-06-02 | 2022-06-05 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Jaipur | Kotputli | Family engagement event | KOTPUTLI- 30 families of contractors; Shoorveer attachment | Avinash Gautam, Akash Rathore | 2022-07-20 | 2022-08-05 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Jaipur | Kotputli | Dedicated BTL van activity | BTL Van for KOTPUTLI tehsil | Avinash Gautam | 2022-05-25 | 2022-06-30 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Jaipur | Kotputli | ARS interest generation meet | KOTPUTLI, PAOTA, KESWANA- Identification + Lunch | Avinash Gautam | 2022-05-25 | 2022-06-20 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Jaipur | Kotputli | Vehicle finance | VEHICLE FINANCE FOR OUR DEALER | Avinash Gautam | 2022-05-20 | 2022-06-20 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Jaipur | Kotputli | Market combing | KOTPUTLI- local; Dealer (85), ARS (120), Contractor (50) | Avinash Gautam, Akash Rathore | 2022-08-14 | 2022-08-25 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Jaipur | Phagi | Dealer onboarding scheme | Dealer Appointment target approx - 1, ARS (2) | Manish Sharma | 2022-05-20 | 2022-06-15 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Jaipur | Phagi | Shoorveer redemption drive | Top 30 contractors > 5000 points | Manish Sharma, Saurabh Chaudhary | 2022-06-02 | 2022-06-05 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Jaipur | Phagi | Mini-depot to prospective dealer | MINI DEPOT TO CS (within Phagi only)- CS to be found | Manish Sharma | 2022-05-25 | 2022-06-20 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Jaipur | Phagi | Family engagement event | PHAGI- 30 families of contractors; Shoorveer attachment | Manish Sharma, Saurabh Chaudhary | 2022-07-15 | 2022-07-28 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Jaipur | Phagi | IBH Buniyaad | PHAGI- 30 IHB | Manish Sharma, Saurabh Chaudhary | 2022-06-15 | 2022-07-05 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Jaipur | Phagi | Contractor scheme | PHAGI- silver & white goods (kind) for 1 quarter funded by BO | Manish Sharma, Saurabh Chaudhary | 2022-07-01 | 2022-09-30 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Jaipur | Phagi | ARS interest generation meet | PHAGI, MADHORAJPURA- Identification + Lunch | Manish Sharma | 2022-07-03 | 2022-07-25 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Jaipur | Phagi | Market combing | PHAGI- local; Dealer (25), ARS (27), Contractor (120) | Manish Sharma, Saurabh Chaudhary | 2022-07-05 | 2022-07-08 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Jaipur | Phulera | Contractor scheme | Dausa- silver & white goods (kind) for 1 quarter funded by BO | Varun Jha, Sunil Chaudhary | 2022-06-15 | 2022-10-15 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Jaipur | Phulera | Family engagement event | Phulera- 30 families of contractors; Shoorveer attachment | Varun Jha, Sunil Chaudhary | 2022-08-05 | 2022-08-25 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Jaipur | Phulera | Dealer onboarding scheme | Dealer Appointment target approx - 2 | Varun Jha | 2022-05-20 | 2022-05-31 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Jaipur | Phulera | Satellite counter | AT JOBNER THROUGH SS | Varun Jha | 2022-06-05 | 2022-06-30 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Jaipur | Phulera | Market combing | PHULERA- local; Dealer (52), ARS (35), Contractor (150+) | Varun Jha, Sunil Chaudhary | 2022-07-15 | 2022-07-28 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Bhilwara | SHAHPURA | IBH Buniyaad | SHAHPURA- 30 IHB | Avinash Gautam, Akash Rathore | 2022-06-15 | 2022-06-20 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Bhilwara | SHAHPURA | Family engagement event | SHAHPURA- 30 families of contractors; Shoorveer attachment | Avinash Gautam, Akash Rathore | 2022-07-17 | 2022-07-20 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Bhilwara | SHAHPURA | Dealer onboarding scheme | Dealer Appointment target approx - 1, June- 2 dealers, ARS (4) | Avinash Gautam | 2022-05-20 | 2022-06-30 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Bhilwara | SHAHPURA | Shoorveer redemption drive | Top 30 contractors > 5000 points | Avinash Gautam, Akash Rathore | 2022-06-02 | 2022-06-05 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Bhilwara | SHAHPURA | Dedicated BTL van activity | BTL Van for Dausa tehsil | Avinash Gautam | 2022-07-01 | 2022-07-04 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Bhilwara | SHAHPURA | Contractor scheme | SHAHPURA- silver & white goods (kind) for 1 quarter funded by BO | Avinash Gautam, Akash Rathore | 2022-06-15 | 2022-10-15 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Bhilwara | SHAHPURA | ARS interest generation meet | SHAHPURA, MANOHAR PURA, ACHROL- Identification + Lunch | Avinash Gautam, Akash Rathore | 2022-07-20 | 2022-07-23 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Bhilwara | SHAHPURA | Market combing | SHAHPURA, MANOHAR PURA, ACHROL- Dealer (50), ARS (70), Contractor (125+) | Avinash Gautam, Akash Rathore | 2022-07-14 | 2022-07-17 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Dausa | Baswa | Contractor scheme | Bandikui- silver & white goods (kind) for 1 quarter funded by BO | Bharat Bhushan, Akash Rathore | 2022-06-01 | 2022-07-30 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Dausa | Baswa | New warehouse | Manpura- 800 MT nearby Sikrai | Bharat Bhushan | 2022-06-15 | 2022-07-20 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Dausa | Baswa | IBH Buniyaad | Bandikui- 30 IHB | Bharat Bhushan, Akash Rathore | 2022-05-27 | 2022-05-31 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Dausa | Baswa | Family engagement event | Bandikui- 30 families of contractors; Shoorveer attachment | Bharat Bhushan, Akash Rathore | 2022-06-12 | 2022-06-12 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Dausa | Baswa | Contractor name branding | Bandikui- Top 10 contractors name branding (Board) | Bharat Bhushan, Akash Rathore | 2022-05-20 | 2022-06-10 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Dausa | Baswa | ARS interest generation meet | Godakatla, Golada, Bandikui- Identification + Lunch; 20-25 Leads | Bharat Bhushan | 2022-07-05 | 2022-07-20 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Dausa | Baswa | Shoorveer redemption drive | Top 30 contractors > 5000 points | Bharat Bhushan, Akash Rathore | 2022-05-23 | 2022-06-10 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Dausa | Baswa | Market combing | Bandikui- local; Dealer (40), ARS (40), Contractor (100) | Bharat Bhushan | 2022-06-15 | 2022-06-28 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Dausa | Dausa | Dealer onboarding scheme | Dealer Appointment target approx - 3 | Bharat Bhushan | 2022-05-20 | 2022-05-31 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Dausa | Dausa | Shoorveer redemption drive | Top 70 contractors > 5000 points | Bharat Bhushan, Akash Rathore | 2022-06-02 | 2022-06-05 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Dausa | Dausa | Family engagement event | Dausa- 30 families of contractors; Shoorveer attachment | Bharat Bhushan, Akash Rathore | 2022-05-25 | 2022-10-06 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Dausa | Dausa | IBH Buniyaad | Dausa - 30 IHB | Bharat Bhushan, Akash Rathore | 2022-06-02 | 2022-06-18 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Dausa | Dausa | Contractor scheme | Dausa- silver & white goods (kind) for 1 quarter funded by BO | Bharat Bhushan, Akash Rathore | 2022-06-01 | 2022-07-30 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Dausa | Dausa | Dedicated BTL van activity | BTL Van for Dausa tehsil | Bharat Bhushan | 2022-06-05 | 2022-06-20 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Dausa | Dausa | ARS interest generation meet | Dausa, Saithal, Jasota, Bhandaraj- Identification + Lunch | Bharat Bhushan | 2022-06-10 | 2022-06-25 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Dausa | Dausa | Contractor name branding | Dausa - Top 10 contractors name branding (Board) | Bharat Bhushan, Akash Rathore | 2022-05-20 | 2022-06-10 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Dausa | Lalsot | Dealer onboarding scheme | Dealer Appointment target approx - 3 | Bharat Bhushan | 2022-05-20 | 2022-05-31 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Dausa | Lalsot | Shoorveer redemption drive | Top 30 contractors > 5000 points | Bharat Bhushan | 2022-06-02 | 2022-06-05 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Dausa | Lalsot | IBH Buniyaad | LALSOT- 30 IHB | Bharat Bhushan | 2022-07-10 | 2022-07-28 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Dausa | Lalsot | Contractor scheme | LALSOT- silver & white goods (kind) for 1 quarter funded by BO | Bharat Bhushan | 2022-07-01 | 2022-07-30 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Dausa | Lalsot | Dedicated BTL van activity | BTL Van for LALSOT tehsil | Bharat Bhushan | 2022-05-25 | 2022-06-30 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Dausa | Lalsot | Market combing | LALSOT, MANDAVRI- local; Dealer (30), ARS (45), Contractor (100) | Bharat Bhushan | 2022-07-01 | 2022-07-15 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Dausa | Sikrai | Family engagement event | SIKRAI- 30 families of contractors; Shoorveer attachment | Bharat Bhushan, Akash Rathore | 2022-08-01 | 2022-08-20 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Dausa | Sikrai | Dedicated BTL van activity | BTL Van for SIKRAI tehsil | Bharat Bhushan | 2022-05-25 | 2022-06-30 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Dausa | Sikrai | Contractor name branding | SIKRAI- Top 10 contractors name branding (Board) | Bharat Bhushan, Akash Rathore | 2022-05-20 | 2022-06-10 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Dausa | Sikrai | New warehouse | Manpura- 800 MT nearby Sikrai | Bharat Bhushan | 2022-06-15 | 2022-07-20 |  | Ongoing
| RJ-1 (Jaipur) | Jaipur Rural | Dausa | Sikrai | Market combing | SIKRAI, SIKANDRA, BALAJI MOD- local; Contractor (80); ARS (5) | Bharat Bhushan, Akash Rathore | 2022-08-01 | 2022-08-18 |  | Ongoing
| RJ-2 (Jodhpur) | Barmer | Barmer | BARMER | Dedicated BTL van activity | Sindhari circle,Chohtan circle,Gadra circle | Shubham Jain, Abhigyan Joshi | 2022-06-05 | 2022-06-17 |  | Delayed
| RJ-2 (Jodhpur) | Barmer | Barmer | BARMER | City express | Inside Barmer city | Shubham Jain | 2022-06-12 | 2022-07-06 |  | Delayed
| RJ-2 (Jodhpur) | Barmer | Barmer | BARMER | Satellite counter | At Chota circle; KUSHUL GURU CEMENT AGENCY | Shubham Jain | 2022-06-02 | 2022-06-30 |  | Delayed
| RJ-2 (Jodhpur) | Barmer | Barmer | BARMER | ARS interest generation meet | 20+ people in meeting; Indraprasth resort-Barmer; 150rs per person expense | Shubham Jain, , Abhigyan Joshi | 2022-06-10 | 2022-07-02 |  | Delayed
| RJ-2 (Jodhpur) | Barmer | Barmer | BARMER | Contractor scheme | BO scheme- silver; Scheme disbursment place (100+ contractors)-Kailash international; 10MT-1RS,30MT-2RS,50MT-4RS | Shubham Jain | 2022-06-10 | 2022-08-12 |  | Delayed
| RJ-2 (Jodhpur) | Barmer | Barmer | PACHPADRA | Market combing | BALOTRA,KALYANPUR,PAREU,GIDA,KANOD Dealer (40); ARS (80); Contractor (200) | Manish, Anil Gaur | 2022-06-05 | 2022-06-14 |  | Delayed
| RJ-2 (Jodhpur) | Barmer | Barmer | PACHPADRA | Dedicated BTL van activity | PACHPADRA,BALOTRA,PATODI; Quiz, game activity to be organised | Manish, Anil Gaur | 2022-06-12 | 2022-06-25 |  | Delayed
| RJ-2 (Jodhpur) | Barmer | Barmer | PACHPADRA | ARS interest generation meet | 20+ ARS; Balota, Lalit Hotel | Manish | 2022-06-06 | 2022-07-01 |  | Delayed
| RJ-2 (Jodhpur) | Barmer | Barmer | SIWANA | Market combing | MOKALSAR,RAKHI,KHANDAP,PADRU; Dealer (35), ARS (60), Contractor (200) | Manish, Anil Gaur | 2022-07-05 | 2022-07-13 |  | Delayed
| RJ-2 (Jodhpur) | Barmer | Barmer | SIWANA | Contractor name branding | Top 7 contractors identified already | Manish, Anil Gaur | 2022-07-05 | 2022-08-04 |  | Delayed
| RJ-2 (Jodhpur) | Barmer | Barmer | SIWANA | Shoorveer redemption drive | 5000+ top contractors; 100+ contractors | Manish, Anil Gaur | 2022-07-04 | 2022-07-25 |  | Delayed
| RJ-2 (Jodhpur) | Jodhpur | Jodhpur | BHOPALGARH | Market combing | Bhopalgarh, Asop, Sevki; Dealer (18), ARS (35), Contractor (300); 2 sets of combing | Shubham Jaiman | 2022-06-05 | 2022-06-20 |  | Delayed
| RJ-2 (Jodhpur) | Jodhpur | Jodhpur | BHOPALGARH | Dedicated BTL van activity | Bhopalgarh, Asop, Sevki; Nukkad, sitevisits, evening meeting (25); DMO, RE, SE to sit in van | Shubham Jaiman, Lal Bahadur | 2022-06-10 | 2022-06-13 |  | Delayed
| RJ-2 (Jodhpur) | Jodhpur | Jodhpur | BHOPALGARH | ARS interest generation meet | Same 3 areas, one each; 10-12 each meeting; Presentation + profitability discussion | Shubham Jaiman | 2022-06-20 | 2022-06-23 |  | Delayed
| RJ-2 (Jodhpur) | Jodhpur | Jodhpur | BHOPALGARH | Dealer onboarding scheme | Bhopalgarh (1 dealer, 4 ARS); Asop (2 ARS), Sevki (2 ARS) | Shubham Jaiman | 2022-05-24 | 2022-06-30 |  | Delayed
| RJ-2 (Jodhpur) | Jodhpur | Jodhpur | BHOPALGARH | Contractor scheme | Same 3 areas; 150 more contractors to be registered; 75 active; BO budget- silver | Shubham Jaiman, Lal Bahadur | 2022-05-24 | 2022-06-30 |  | Delayed
| RJ-2 (Jodhpur) | Jodhpur | Jodhpur | BHOPALGARH | Satellite counter | Through BO (Naveen Distributor)- Bhopalgarh | Shubham Jaiman | 2022-06-01 | 2022-06-30 |  | Delayed
| RJ-2 (Jodhpur) | Jodhpur | Jodhpur | BHOPALGARH | Tranformative branding | Sharing boards in three areas | Puneet Agnihotri, Shubham Jaiman | 2022-06-01 | 2022-06-30 |  | Delayed
| RJ-2 (Jodhpur) | Jodhpur | Jodhpur | BHOPALGARH | BO Revamp | Naveen distb (QMP- Satellite counter, 3 dealer, 6 ARS, Re1 on Mar to Jun sales on MD activities) | Puneet Agnihotri, Shubham Jaiman | 2022-06-01 | 2022-06-30 |  | Delayed
| RJ-2 (Jodhpur) | Jodhpur | Nagaur | Didwana | Market combing | Choti Khatu, Didwana, Molasar, Dhaulatpur, Dhankoli; Dealer (30+), ARS (60+), Contractor (400+); 2 sets of combing | Deepak Dadhich, Lal Bahadur | 2022-06-10 | 2022-06-30 |  | Delayed
| RJ-2 (Jodhpur) | Jodhpur | Nagaur | Didwana | Dedicated BTL van activity | Same areas; Nukkad, sitevisits, evening meeting (25); DMO, RE, SE to sit in van | Deepak Dadhich, Lal Bahadur | 2022-06-10 | 2022-06-30 |  | Delayed
| RJ-2 (Jodhpur) | Jodhpur | Nagaur | Didwana | Dealer onboarding scheme | Dealer (2), ARS (5) | Deepak Dadhich | 2022-06-01 | 2022-06-30 |  | Delayed
| RJ-2 (Jodhpur) | Jodhpur | Nagaur | Didwana | ARS interest generation meet | 10-12 in meeting; 1 meeting | Deepak Dadhich | 2022-06-01 | 2022-06-30 |  | Delayed
| RJ-2 (Jodhpur) | Jodhpur | Nagaur | Didwana | Contractor name branding | Same areas; Marketing information | Lal Bahadur | 2022-06-01 | 2022-06-30 |  | Delayed
| RJ-2 (Jodhpur) | Jodhpur | Nagaur | Didwana | Contractor scheme | Bo funded- silver | Deepak Dadhich, Lal Bahadur | 2022-06-15 | 2022-07-30 |  | Delayed
| RJ-2 (Jodhpur) | Jodhpur | Nagaur | Jayal | Market combing | Tarnau Dugoli, Firodh, Jayal; Dealer (20+), ARS (40+), Contractor (100+) | Kapil Pareek, Lal Bahadur | 2022-07-03 | 2022-07-06 |  | Delayed
| RJ-2 (Jodhpur) | Jodhpur | Nagaur | Jayal | Dedicated BTL van activity | Nukkad, sitevisits, evening meeting (25); DMO, RE, SE to sit in van | Kapil Pareek, Lal Bahadur | 2022-07-03 | 2022-07-06 |  | Delayed
| RJ-2 (Jodhpur) | Jodhpur | Nagaur | Jayal | Contractor scheme | Bo funded- silver | Kapil Pareek, Lal Bahadur | 2022-06-15 | 2022-07-30 |  | Delayed
| RJ-2 (Jodhpur) | Jodhpur | Nagaur | Jayal | Dealer onboarding scheme | Dealer (1); ARS (3) | Kapil Pareek | 2022-06-01 | 2022-06-30 |  | Delayed
| RJ-2 (Jodhpur) | Jodhpur | Nagaur | Jayal | IBH Buniyaad | 100+ visits; meetings; name plate for good houses | Kapil Pareek, Lal Bahadur | 2022-07-01 | 2022-08-15 |  | Delayed
| RJ-2 (Jodhpur) | Jodhpur | Nagaur | Nagaur | Market combing | Mudwa, Kuchera, Butati; Dealer (38), ARS (70), Contractor (200 registrations) | Kapil Pareek, Lal Bahadur | 2022-06-05 | 2022-06-08 |  | Delayed
| RJ-2 (Jodhpur) | Jodhpur | Nagaur | Nagaur | Dedicated BTL van activity | Same 3; Nukkad, sitevisits, evening meeting (20); DMO, RE, SE to sit in van | Kapil Pareek, Lal Bahadur | 2022-06-15 | 2022-06-15 |  | Delayed
| RJ-2 (Jodhpur) | Jodhpur | Nagaur | Nagaur | IBH Buniyaad | 200 IHB visits; 2 meetings of 30 each | Kapil Pareek, Lal Bahadur | 2022-06-18 | 2022-06-20 |  | Delayed
| RJ-2 (Jodhpur) | Jodhpur | Nagaur | Nagaur | Dealer onboarding scheme | 3 Dealers & 7 ARS | Kapil Pareek | 2022-05-24 | 2022-06-30 |  | Delayed
| RJ-2 (Jodhpur) | Jodhpur | Nagaur | Nagaur | Contractor scheme | 200+ registrations; 70+ activations; BO scheme- silver, kind | Kapil Pareek, Lal Bahadur | 2022-06-01 | 2022-06-30 |  | Delayed
| RJ-2 (Jodhpur) | Jodhpur | Nagaur | Nagaur | BO Revamp | Baba Ram Dev (QMP- 3 dealer, 7 ARS, Re1 on Mar to Jun sales on MD activities) | Kapil Pareek | 2022-05-24 | 2022-06-30 |  | Delayed
| RJ-2 (Jodhpur) | Jodhpur | Nagaur | Nawa | Market combing | Mithari, Nawa, Rajliya; Dealer (40+), ARS (80+), Contractor (200+) | Deepak Dadhich, Lal Bahadur | 2022-07-10 | 2022-07-15 |  | Delayed
| RJ-2 (Jodhpur) | Jodhpur | Nagaur | Nawa | Dedicated BTL van activity | Same areas | Deepak Dadhich, Lal Bahadur | 2022-07-10 | 2022-07-15 |  | Delayed
| RJ-2 (Jodhpur) | Jodhpur | Nagaur | Nawa | Contractor name branding | Same areas; Marketing information | Deepak Dadhich, Lal Bahadur | 2022-07-15 | 2022-07-20 |  | Delayed
| RJ-2 (Jodhpur) | Jodhpur | Nagaur | Nawa | IBH Buniyaad | 200 IHB visits; 2 meetings of 30 each | Deepak Dadhich, Lal Bahadur | 2022-07-15 | 2022-07-20 |  | Delayed
| RJ-2 (Jodhpur) | Jodhpur | Nagaur | Nawa | Dealer onboarding scheme | Dealer (3); ARS (5) | Deepak Dadhich | 2022-06-01 | 2022-07-30 |  | Delayed
| RJ-2 (Jodhpur) | Jodhpur | Nagaur | Nawa | Contractor scheme | Bo funded- silver | Deepak Dadhich, Lal Bahadur | 2022-07-15 | 2022-08-30 |  | Delayed
| RJ-2 (Jodhpur) | Jodhpur | Nagaur | Nawa | ARS interest generation meet | 10-12 in meeting; 1 meeting | Deepak Dadhich, Lal Bahadur | 2022-07-17 | 2022-07-30 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Jalore | Bhinmal | Market combing | Bhinmal, Jaswantpura, Ramsen, Punasa, Pathedi; Dealer (58), ARS (50), Contractor (200 registrations) | Brahmdutt, Sewaram | 2022-06-01 | 2022-06-20 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Jalore | Bhinmal | Dedicated BTL van activity | Same as above; Nukkad, sitevisits, evening meeting (40); DMO, RE, SE to sit in van | Brahmdutt, Sewaram | 2022-06-07 | 2022-06-10 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Jalore | Bhinmal | ARS interest generation meet | 50 in one meeting; Presentation + profitability discussion | Brahmdutt, Sewaram | 2022-06-10 | 2022-06-30 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Jalore | Bhinmal | Contractor scheme | 381 existing + 200 new; BO funded- silver | Brahmdutt, Sewaram | 2022-06-01 | 2022-06-20 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Jalore | Bhinmal | Dealer onboarding scheme | Bhinmal, Jaswantpura, Punasa, Pathedi; 3 dealers & 10 ARS | Brahmdutt | 2022-05-24 | 2022-06-30 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Jalore | Bhinmal | Contractor name branding | Bhinmal, Jhunjhani, Ramsen, Modera; Boards, nameplate, POP | Brahmdutt, Sewaram | 2022-06-01 | 2022-06-30 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Jalore | Bhinmal | Shoorveer redemption drive | 5000+ points; 100 contractors | Brahmdutt, Sewaram | 2022-08-01 | 2022-08-25 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Jalore | Jalore | Market combing | Siyana, Akuli + nearby areas; Dealers (10), ARS (15), Contractors (100 registrations) | Anurag Mishra, Sewaram | 2022-06-22 | 2022-06-25 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Jalore | Jalore | Dedicated BTL van activity | Same as above; Nukkad, sitevisits, evening meeting (25); DMO, RE, SE to sit in van | Anurag Mishra, Sewaram | 2022-06-25 | 2022-07-03 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Jalore | Jalore | ARS interest generation meet | 25 in one meeting; Presentation + profitability discussion | Anurag Mishra, Sewaram | 2022-07-05 | 2022-07-05 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Jalore | Jalore | Contractor scheme | Existing + 75 new; BO- silver | Anurag Mishra, Sewaram | 2022-06-01 | 2022-06-30 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Jalore | Jalore | Shoorveer redemption drive | 5000+ points; 100 contractors | Sewaram | 2022-06-04 | 2022-06-10 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Jalore | Raniwara | Market combing | Raniwara, Malwada, Karda, Badgaon; Dealer (25), ARS (40), Contractor (75 registrations) | Brahmdutt, Sewaram | 2022-07-01 | 2022-07-30 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Jalore | Raniwara | Dedicated BTL van activity | Same as above; Nukkad, sitevisits, evening meeting (20); DMO, RE, SE to sit in van | Brahmdutt, Sewaram | 2022-06-07 | 2022-06-10 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Jalore | Raniwara | ARS interest generation meet | 50 in one meeting; Presentation + profitability discussion | Brahmdutt, Sewaram | 2022-07-10 | 2022-07-30 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Jalore | Raniwara | Contractor scheme | 50+ existing + 75 new; BO funded- silver | Brahmdutt, Sewaram | 2022-07-01 | 2022-07-20 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Jalore | Raniwara | Dealer onboarding scheme | Karda, Raniwara, Rajikawas; 1 dealer & 5 ARS | Brahmdutt | 2022-05-24 | 2022-06-30 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Jalore | Sayla | Market combing | City, Chauru, Bawatra, Jiwana, Posana; Dealer (35), ARS (28), Contractor (100 registrations) | Anurag Mishra, Sewaram | 2022-01-07 | 2022-07-10 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Jalore | Sayla | Dedicated BTL van activity | Same areas | Anurag Mishra, Sewaram | 2022-07-12 | 2022-07-15 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Jalore | Sayla | ARS interest generation meet | 25 in one meeting; Presentation + profitability discussion | Anurag Mishra, Sewaram | 2022-08-30 | 2022-08-30 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Jalore | Sayla | Contractor scheme | 50+ existing + 75 new; BO funded- silver | Anurag Mishra, Sewaram | 2022-07-01 | 2022-07-30 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Jalore | Sayla | Contractor name branding | Across large contractors, common areas | Anurag Mishra, Sewaram | 2022-09-01 | 2022-09-15 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Jalore | Sayla | Dealer onboarding scheme | 2 dealer, 5 ars | Anurag Mishra | 2022-06-01 | 2022-06-30 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Pali | JAITARAN | Dealer onboarding scheme | Ananpur Kalu, Lambia; 3 dealer & 6 ARS | Jaideep Paliwal | 2022-05-24 | 2022-06-30 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Pali | JAITARAN | ARS interest generation meet | 25 in one meeting; Presentation + profitability discussion | Jaideep Paliwal, Mohit Mathur | 2022-05-24 | 2022-06-05 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Pali | JAITARAN | Satellite counter | Dev Nakhoda Cement agency- Kudki | Jaideep Paliwal | 2022-05-24 | 2022-06-15 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Pali | SOJAT | Market combing | City + outskirts; Dealer (25), ARS (40), Contractor (100+ registrations) | Jaideep Paliwal, Madhusudan | 2022-05-24 | 2022-06-30 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Pali | SOJAT | ARS interest generation meet | 20 potential ARS; Same as above; Influencer led event | Jaideep Paliwal, Madhusudan | 2022-05-24 | 2022-06-30 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Pali | SOJAT | Shoorveer redemption drive | 20+ contractors above 10k points | Mohit Mathur | 2022-06-01 | 2022-06-30 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Pali | SOJAT | IBH Buniyaad | Slab supervision; 10+ people; 1 IHB meet | Mohit Mathur | 2022-05-24 | 2022-06-30 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Pali | SUMERPUR | Market combing | Nana, Beda, Baluna, Bijapur; Dealer (32), ARS (40), Contractor (150+ registrations) | Aman Sharma, Mohit Mathur | 2022-06-07 | 2022-06-07 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Pali | SUMERPUR | ARS interest generation meet | Same areas, 10-12 one meeting; Presentation + profitability discussion | Aman Sharma, Mohit Mathur | 2022-06-10 | 2022-06-30 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Pali | SUMERPUR | Dealer onboarding scheme | City, Bijapur; 1 dealer + 5 ARS | Aman Sharma | 2022-05-24 | 2022-06-30 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Pali | SUMERPUR | Shoorveer redemption drive | 20+ contractors (5000+ points | Mohit Mathur | 2022-06-01 | 2022-06-30 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Sirohi | Sheoganj | Market combing | Shoeganj, Kailashnagar, Jawal & Arathwara; Dealer (30+), ARS (50+), Contractors (200+) | Bhupesh Joshi | 2022-06-11 | 2022-06-19 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Sirohi | Sheoganj | Dedicated BTL van activity | Same areas as above + Joyala, Jogapura, Pausalia; Labour chowk, counter wise, site wise, contractor meeting at the evening | Shubham Khatik | 2022-06-16 | 2022-06-20 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Sirohi | Sheoganj | ARS interest generation meet | 15 potential ARS; Same 4 areas as above; Influencer led event | Bhupesh Joshi | 2022-08-08 | 2022-08-15 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Sirohi | Sheoganj | Contractor name branding | 30 high potential contractors; Board, branding, painting | Shubham Khatik | 2022-07-02 | 2022-07-15 |  | Delayed
| RJ-2 (Jodhpur) | Pali | Sirohi | Sheoganj | New warehouse | Sheoganj warehouse; Location, TDC working closed | Bhupesh Joshi, Avinash Patni | 2022-07-02 | 2022-07-15 |  | Delayed

## Sheet1
Chomu combing- 10th June